## User Stories (+issues stories)
SNO | User | Module | User Stories | Sprint No | Team members | Similar Concept | Priority | Status | No. of test cases | No. of Test scripts file name | Data-cy Status | Defects
1 | Public User | Home page - Public User | As a public user, I want to view CEPI application, and then to view all the home page components. | 1 | Karpagam/Bhuvana | No | High | Done | 9 | 1 | Added
2 | Public User | Home page - Public User | As a public user, I want to access all focus areas individually on home page to view the projects listed under that. | 1 | Bhuvana | No | High | Done | 7 | 1 | Added
3 | Public User | Maps - Public User | As a public user, I want to view the Maps for Community partners with respect to the selected filters and then view the total number of community partners. | 1 | Shireen | No | High | Done | 5
4 | Public User | Maps - Public User | As a public user, I want to view the Maps for Legislative districts with respect to the selected filters and and then view the total number of community partners. | 2 - replan | Naga | No | High | Done | 6
5 | Public User | Maps - Public User | As a public user, I want to view the Maps for City districts with respect to the selected filters and and then view the total number of community partners. | 2 - replan | Naga | No | High | Done | 6
6 | Public User | Maps - Public User | As a public user, I want to view the Maps for Community partner types with respect to the selected filters and and then view the total number of community partners. | 2 - replan | Shireen | No | High | Done | 5
7 | Public User | Maps - Public User | As a public user, I want to view the Maps for Projects engaged with respect to the selected filters and and then view the total number of community partners. -- | 2 | Naga | No | High | Done | 3
8 | Public User | Analytics - Reports - Public User | As a public user, I want to view the Reports for Focus Area with respect to the selected filter under Analytics tab in navigation menu bar. | 1 | Karpagam | No | High | Done | 10
9 | Public User | Analytics - Reports - Public User | As a public user, I want to view the Reports for Engagement types with respect to the selected filter under Analytics tab in navigation menu bar. | 1 | Karpagam | No | High | Done | 10
10 | Public User | Analytics - Reports - Public User | As a public user, I want to view the Reports for Community partners with respect to the selected filter under Analytics tab in navigation menu bar. | 1 | Rama | No | High | Done | 7
11 | Public User | Analytics - Reports - Public User | As a public user, I want to view the Reports for Projects with respect to the selected filter under Analytics tab in navigation menu bar. | 2 - replan | Karpagam | No | High | Done | 7
12 | Public User | Analytics - Charts - Public User | As a public user, I want to view the Charts for Focus area with respect to the selected filter under Analytics tab in navigation menu bar. | 2 - replan | Diana | No | High | Done | 8
13 | Public User | Analytics - Charts - Public User | As a public user, I want to view the Charts for Engagement types with respect to the selected filter under Analytics tab in navigation menu bar. | 2 - replan | Bhuvana | No | High | Done | 8 | 1
14 | Public User | Partners - Register Campus Partner - Public User | As a public user, I want to access the link "Register campus Partner" under partners menu in navigation bar to register as a campus partner user. -- | Deferred to 2 | Bhuvana | No | High | Done | 17 | 1
15 | Public User | Resources - Public User | As a public user, I want to navigate to resources menu in navigation bar to view the external links which is providing additional information about this initiative. | 1 | Rama | No | High | Done | 5
16 | Campus partner | Home page - Campus Partner | As a campus partner user, I want to view CEPI application, and then to view all the home page components. Campus partner has additional option Projects Menu. | 3 | Karpagam/Bhuvana | Yes | Medium | Done | 12 | ../homepage/homepageCampusPartnerUser.cy.js | Added
17 | Campus partner | Home page - Campus Partner | As a campus partner user, I want to access all focus areas individually to view the projects listed under that. | 3 | Bhuvana | Yes | Medium | Done | 7 | ../homepage/allFocusAreaCampusUser.cy.js | Added
18 | Campus partner | Maps - Campus Partner | As a campus partner user, I want to view the Maps for Community partners with respect to the selected filters and then view the total number of community partners. -- | 2 | Naga | Yes | Medium | Done | 9
19 | Campus partner | Maps - Campus Partner | As a campus partner user, I want to view the Maps for Legislative districts with respect to the selected filters and and then view the total number of community partners. | 3 | Naga | Yes | Medium | Done | 2 | ../maps/legislativeDistrictMapsCampusPartner.cy | Added
20 | Campus partner | Maps - Campus Partner | As a campus partner user, I want to view the Maps for City districts with respect to the selected filters and and then view the total number of community partners. | 3 | Naga | Yes | Medium | Done |  |  | Added
21 | Campus partner | Maps - Campus Partner | As a campus partner user, I want to view the Maps for Community partner types with respect to the selected filters and and then view the total number of community partners. | 4 | Naga | Yes | Medium
22 | Campus partner | Maps - Campus Partner | As a campus partner user, I want to view the Maps for Projects engaged with respect to the selected filters and and then view the total number of community partners. | 4 | Naga | Yes | Medium
23 | Campus partner | Partners - Register Campus Partner - Campus Partner | As a campus partner, I want to access the link "Register campus Partner" under partners menu in navigation bar to register as a campus partner user. -- | 2 | Karpagam | Yes | Medium | Done | 4
24 | Campus partner | Projects - Campus Partner | As a campus partner user, I want to access Projects menu in the navigation bar to view all projects and my projects. | 2 | Shireen | No | High | Done | 19
| Campus partner | Projects - Campus Partner | As a campus partner user, I want to access Projects menu in the navigation bar to create the projects. | 2 | Bhuvana |  |  | Done | 17 | 1
| Campus partner | Projects - Campus Partner | As a campus partner user, I want to access Projects menu in the navigation bar to edit/delete the project from My Drafts. | 2 | Karpagam |  |  | Done | 4
25 | Campus partner | Analytics - Reports - Campus Partner | As a campus partner user, I want to view the Reports for Focus Area with respect to the selected filter under Analytics tab in navigation menu bar. -- | 2 | Karpagam | Yes | Medium | Done | 11
26 | Campus partner | Analytics - Reports - Campus Partner | As a campus partner user, I want to view the Reports for Engagement types with respect to the selected filter under Analytics tab in navigation menu bar. | 3 | Karpagam | Yes | Medium | Done | 9 | ../analytics/reports/engagementTypesReportsCampusPartnerUser.cy.js | Added
27 | Campus partner | Analytics - Reports - Campus Partner | As a campus partner user, I want to view the Reports for Community partners with respect to the selected filter under Analytics tab in navigation menu bar. | 3 | Rama | Yes | Medium | Done | 9 | ../analytics/reports/CommunityPartnerReportsCampusUser.cy.js | Added
28 | Campus partner | Analytics - Reports - Campus Partner | As a campus partner user, I want to view the Reports for Projects with respect to the selected filter under Analytics tab in navigation menu bar. | 3 | Naga | Yes | Medium | Done | 1 | ../analytics/reports/projectsReportsCampusUser.cy.js | Added
29 | Campus partner | Analytics - Charts - Campus Partner | As a campus partner user, I want to view the charts for Focus Area and projects/community partners with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
30 | Campus partner | Analytics - Charts - Campus Partner | As a campus partner user, I want to view the charts for Engagement types and projects/partners with respect to the selected filter under Analytics tab in navigation menu bar. | 3 | Bhuvana | Yes | Medium | Done | 7 | analytics/charts/engagementTypesChartsCampusPartnerUser.cy.js | Added
31a | Campus partner | Analytics - Charts - Campus Partner | As a campus partner, I want to access charts under Analytics menu, and then to see the charts for Focus area analysis | 3 | Anh |  |  | Done | 6 | ../analytics/charts/focusAreaChartsCampusPartner.cy.js | Added
31b | Campus partner | Analytics - Charts - Campus Partner | As a campus partner, I want to access charts under Analytics menu, and then to see the charts for Network Analysis | Deferred to 4 | Karpagam |  |  | Done |  |  | Added
31c | Campus partner | Analytics - Charts - Campus Partner | As a campus partner, I want to access charts under Analytics menu, and then to see the charts for Partnership instensity analysis. | 3 | Shireen | No | Medium | Done | 4 |  | Added
32 | Campus partner | Resources - Campus Partner | As a campus partner user, I want to navigate to resources menu in navigation bar to view the external links which is providing additional information about this initiative. | 3 | Rama | Yes | Low | Done | 6 |  | Added
33 | Campus partner | Login - Campus Partner | As an campus partner user, I want to login to CEPI application by entering a valid username and password. -- | Deferred to 2 | Shireen | No | Low | Done | 3
34 | Campus partner | Logout - Campus user | As a campus partner user, I want to logout of the CEPI application using the Logout option in the Navigation menu items. -- | Deferred to 2 | Shireen | No | Low | Done | 1
35 | Campus partner | Password Reset - Campus user | As a campus partner user, I want to reset password in case the user forgot the password | 4 |  | No | Low
36 | Campus partner | User profile update - campus partner | As a campus partner, I want to update my user details by accessingnthe "My Profile" page from clicking the user icon. | 3 | Diana | No | Low | Done | 2 |  | Added
37 | Administrator | Home Page - Administrator | As an public user, I want to view CEPI application, and then to view all the home page components. Administrator has additional option for Administrator and Projects Menu. | 3 | Karpagam/Bhuvana | Yes | Medium | Done | 11 | ../homepage/homepageAdministrator.cy.js | Added
38 | Administrator | Home Page - Administrator | As an administrator, I want to access all focus areas individually on home page to view the projects listed under that. | 3 | Bhuvana | Yes | Medium | Done | 7 | ../homepage/allFocusAreaAdminUser.cy.js | Added
39 | Administrator | Maps - Administrator | As an administrator, I want to view the Maps for Community partners with respect to the selected filters and then view the total number of community partners. | 3 | Shireen | Yes | Medium | Done | 9 |  | Added
40 | Administrator | Maps - Administrator | As an administrator, I want to view the Maps for Legislative districts with respect to the selected filters and and then view the total number of community partners. | 3 | Naga | Yes | Medium | Done | 2 |  | Added
41 | Administrator | Maps - Administrator | As an administrator, I want to view the Maps for City districts with respect to the selected filters and and then view the total number of community partners. | 4 | Naga | Yes | Medium
42 | Administrator | Maps - Administrator | As an administrator, I want to view the Maps for Community partner types with respect to the selected filters and and then view the total number of community partners. | 4 | Shireen | Yes | Medium
43 | Administrator | Maps - Administrator | As an administrator, I want to view the Maps for Projects engaged with respect to the selected filters and and then view the total number of community partners. | 4 | Naga | Yes | Medium
44 | Administrator | Analytics - Reports - Administrator | As an administrator, I want to view the Reports for Focus Area with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
45 | Administrator | Analytics - Reports - Administrator | As an administrator, I want to view the Reports for Engagement types with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
46 | Administrator | Analytics - Reports - Administrator | As an administrator, I want to view the Reports for Community partners with respect to the selected filter under Analytics tab in navigation menu bar. | 4 | Rama | Yes | Medium | Done
47 | Administrator | Analytics - Reports - Administrator | As an administrator, I want to view the Reports for Projects with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
48 | Administrator | Analytics - Charts - Administrator | As an administrator, I want to view the charts for Focus Area and projects/community partners with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
49 | Administrator | Analytics - Charts - Administrator | As an administrator, I want to view the charts for Engagement types and projects/partners with respect to the selected filter under Analytics tab in navigation menu bar. | 4 |  | Yes | Medium
50a | Administrator | Analytics - Charts - Administrator | As an administrator, I want to access charts under Analytics menu, and then to see the charts for focus area analysis | 3 | Anh | Yes | Medium | Done | 6 | 1 | Added
50b | Administrator | Analytics - Charts - Administrator | As an administrator, I want to access charts under Analytics menu, and then to see the charts for Project and partner trends | 3 | Anh | Yes | Medium | Done | 6 | 1 | Added
50c | Administrator | Analytics - Charts - Administrator | As an administrator, I want to access charts under Analytics menu, and then to see the charts for Network Analysis | Deferred to 4 | Karpagam | Yes | Medium | Deferred
50d | Administrator | Analytics - Charts - Administrator | As an administrator, I want to access charts under Analytics menu, and then to see the charts for partnership instensity analysis | 3 | Shireen | Yes | Medium | Done | 4 |  | Added
51 | Administrator | Projects - Administrator | As an administrator, I want to access Projects menu in the navigation bar to view all projects and my projects. | Deferred to 3 | Shireen | Yes | High | Done | 10 |  | Added
| Administrator | Projects - Administrator | As an administrator, I want to access Projects menu in the navigation bar to create the projects. | Deferred to 3 | Bhuvana | Yes |  | Done | 17 | 1 | Added
| Administrator | Projects - Administrator | As an administrator, I want to access Projects menu in the navigation bar to edit/delete the project from My Drafts. | Deferred to 3 | Karpagam | Yes |  | Done | 5 | ../projects/myDraftAdministrator.cy.js | Added
52 | Administrator | Partners - Administrator | As an administrator, I want to access register as a campus partner by clicking the Partners menu in the navigaton bar -- | 2 | Anh | Yes | Medium | Done | 17
53 | Administrator | Resources - Administrator | As an admin user, I want to access resources, then to view the resources list as required in the future. | 3 | Rama | Yes | Low | Done | 6 |  | Added
54 | Administrator | Admin Panel | As an admin user, I want to create user by using 'Campus Partner User Registration" menu under Administrator tab. -- | Deferred to 2 | Diana | No | Medium | Done | 2
55 | Administrator | Admin panel | As an admin user, I want to access the CMS option to manage the home page content without relying on development team. | 3 | Diana | No | Low | Pending | 14 |  | Added
56 | Administrator | Admin Panel | As an admin user, I want to access 'Organization' menu under Administrator tab to view the list of community partners. -- | Deferred to 2 | Diana | No | Low | Done | 7
56 | Administrator | Admin panel | As an admin user, I want to access 'Audit logs' menu under Administrator tab to view the Audit logs | Deferred to 4 |  | No | Low
58 | Administrator | Admin Panel | As an admin user, I want to access 'Admin View' menu under Administrator tab to use the admin panel and make necessary admin home activities -- | Deferred to 2 | Diana | No | Low | Done | 50
59 | Administrator | Logout - Administrator | As an admin user, I want to logout of the CEPI application using the Logout option in the Navigation menu items -- | Deferred to 2 | Shireen | Yes | Low | Done | 1
60 | Administrator | Login - Administrator | As an admin user, I want to login to CEPI application by entering a valid username and password -- | Deferred to 2 | Shireen | Yes | Low | Done | 3
61 | Administrator | Password Reset - Administrator | As an administrator, I want to reset password in case the user forgot the password | 4 |  | Yes | Low

## Users & Privileges
High Level Scenarios | User
| Public User | Campus Partner | Administrator | Priority
Home page | X | X | X | 1
Maps - Community partners | X | X | X | 2
Maps - Legislative districts | X | X | X | 2
Maps - City districts | X | X | X | 3
Maps - Communitive partner | X | X | X | 3
Maps - Projects | X | X | X | 2
Analytics - Reports - Focus Area | X | X | X | 2
Analytics - Reports - Engagement types | X | X | X | 3
Analytics - Reports - Community partners | X | X | X | 3
Analytics - Reports - Projects | X | X | X | 2
Analytics - Charts - Focus Areas | X | X | X | 2
Analytics - Charts - Engagement types | X | X | X | 2
Analytics - Charts - Focus Areas Analysis |  | X | X | 3
Analytics - Charts - Projects and Partner Trends |  | X | X | 3
Analytics - Charts - Network analysis |  | X | X | 3
Analytics - Charts - Partnership Intensity Analysis |  | X | X | 3
Projects - All Projects |  | X | X | 2
Projects - My Projects |  | X |  | 1
Projects - Create rojects |  | X | X | 1
Proiect - Edit/Delete from front end? |  | X | X | 3
Projects - My drafts |  | X | X | 1
Admin Panal - Admin View - CRUD |  |  | X | 1
Admin Panal - CMS |  |  | X | 1
Admin Panal - Organization |  |  | X | 3
Admin Panal - Audit Logs |  |  | X | 3
Admin Panal - Campus partner registration |  |  | X | 1
Login/Logout |  | X | X | 2
Password Reset |  | X | X | 2

## Metrics
Sprint 1
[10 empty] | Functionality | Test Cases
Planned | Total User Stories | Planned | Replanned | Deferred | Deferred but completed | Completed | Completed % |  |  | Community Partners | 5
User Stories | 61 | 15 | 6 | 8 | 4 | 13 | 21.31% |  |  | Community Partner Types | 5
Test Cases | [5 empty] | 90 |  |  |  | Legislative District | 6
[10 empty] | City District | 6
[10 empty] | Home page components | 9
Defects Identified ​ | 2​ | [8 empty] | Focus Area Cards | 4
#2333 , #2310​ | [9 empty] | Focus Area Reports | 10
Impacted User Stories​ | 3 + (1)​ | [8 empty] | Engagement Types Reports | 10
[10 empty] | Projects Reports | 7
[10 empty] | Communuty Partner Reports | 7
[10 empty] | External links | 5
[10 empty] | Focus Area Charts | 8
[10 empty] | Engagement Types Charts | 8
Sprint 2
Planned | Total User Stories | Planned | Replanned | Deferred | Deferred but completed | Completed | Completed %
User Stories | 61 | 16 | 0 | 0 | 0 | 16 | 26.23%
Test Cases | [5 empty] | 187
[8 empty] | User | Feature | Functionality | Test Cases
[8 empty] | campus partner user | Maps | Projects maps | 3
Defects Identified ​ | 7 | [8 empty] | Community partners | 9
Impacted User Stories​ | 5 | [7 empty] | Register partners | Register campus partner | 4
#2394, #2371, #2369, #2365, #2364, #2395, #2396 | [8 empty] | Reports | Focus area | 11
[9 empty] | Projects | Create projects | 16
[10 empty] | MyDrafts | 4
[10 empty] | Myprojects | 7
[10 empty] | All projects | 12
[8 empty] | Public user | Register partners | Register campus partner | 17
[9 empty] | Maps | Community partner | 9
[10 empty] | Community partner types | 9
[10 empty] | Project maps | 3
[9 empty] | Login/Logout | Loginadminpanel | 1
[10 empty] | loginAdminFront | 3
[10 empty] | loginCampuspartner | 3
[10 empty] | logoutAdminfront | 1
[10 empty] | logoutCampuspartner | 1
[8 empty] | admin user | Admin view | contact | 7
[10 empty] | data definition | 7
[10 empty] | data definition groups | 7
[10 empty] | household income | 7
[10 empty] | mission area | 7
[10 empty] | resources | 7
[10 empty] | users | 7
[9 empty] | CampuspartnerRegistration | CampuspartnerRegistration | 2
[9 empty] | Organization | CampuspartnerOrganization | 7
[9 empty] | Register partners | Register campus partner | 16
187
Sprint 3
Planned | Total User Stories | Planned | Replanned | Deferred | Deferred but completed | Completed | Completed % | User | Feature | Functionality | Test Cases
User Stories
Test Cases
[8 empty] | admin user | Admin view
cms
profile

## Community partner stories (hidden)
As a community Partner, I want to navigate to the Community partner registration by clicking the Partners menu in navigation bar to create the user.
As a community partner user, I want to access the focus area reports under Analyticas menu, then to drill down on the each focus area details.
As a community partner user, I want to access Projects menu in the navigation bar to view all projects, my projects and to add/ edit/ delete the projects/ drafts.
As a community partner user, I want to access charts under Analytics menu, and then to see the charts for focus area analysis, project and partner trends, network analysis, partnership instensity analysis, and interdesciplinary score. | Check with client /consultant to check whether this is a valid requirement.
As a community partner user, I want to view CEPI application, and then to view all the home page components.
As a community partner user, I want to view the Maps for Community partners with respect to the selected filters and then view the total number of community partners.
As a community partner user, I want to view the Maps for Legislative districts with respect to the selected filters and and then view the total number of community partners.
As a community partner user, I want to view the Maps for City districts with respect to the selected filters and and then view the total number of community partners.
As a community partner user, I want to view the Maps for Communitive partner districts with respect to the selected filters and and then view the total number of community partners.
As a community partner user, I want to view the Maps for Projects engaged with respect to the selected filters and and then view the total number of community partners.
As a community partner user, I want to view the Reports for Focus Area with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to view the Reports for Engagement types with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to view the Reports for Community partners with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to view the Reports for Projects with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to view the charts for Focus Area and projects/community partners with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to view the charts for Engagement types and projects/partners with resepect to the selected filter under Analytics tab in navigation menu bar.
As a community partner user, I want to navigate to resources menu in navigation bar to view the external links which is providing additional information about this initiative.
As a community partner user, I want to access all focus areas one by one to view the projects listed under that.
As a community partner user, I want to access the link view the coomunity partner legislative map, to view the community partners locations in the Nebraska legislative district map.
As a community partner user, I want to access the link view partner and project analysis by focus area to see collabarated report for all focus areas.
As a community partner user, I want to access the link Community engagement at the bottom of the home page to view engagement site of UNO
As a community partner user, I want to access the link CEPI information and guidelines to know about other information and the prescribed guidleines about this initiative.

## Open Issues
S/NO | Module | Issue Description | Screenshot link (Search Issue <issue number> | User | URL | Member | Issue | Production | Date | Status | Recorded by | Comments | Closed Date | Closed by
1 | Maps | City District map is not loading DoesNotExist at /city-District DataDefinition matching query does not exist. Exception Type: DoesNotExist Exception Value: DataDefinition matching query does not exist. Exception Location: C:\Users\kvelayutham\AppData\Local\Programs\Python\Python39\lib\site-packages\django\db\models\query.py, line 650, in get Raised during: home.views.googlecityDistrict | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | All |  | Sakthi | Issue | Working fine | 2023-02-11 | Open
2 | Home page | VIEW THE COMMUNITY PARTNER LEGISLATIVE MAP link is not working Page not found (404) Request Method: GET Request URL: https://uno-cpi.herokuapp.com/legislativeDistrict/ Raised by: wagtail.views.serve | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | All | https://uno-cpi.herokuapp.com/legislativeDistrict/ | Anh/Diana | Issue | Working fine | 2023-02-11 | Open |  | Check with Mansi
3 | Home page | Link to CAMPUS USER GUIDELINES not working Shows a access denied error | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | All |  | Simran | Issue | Issue Page not found error | 2023-02-11 | Open
5 | Analytics - Charts | Focus area chart not opening. KeyError at /missionchart/ 'mission_color' Request Method: GET Request URL: http://127.0.0.1:8000/missionchart/ Django Version: 4.1.2 Exception Type: KeyError Exception Value: 'mission_color' Exception Location: C:\Karpagam\Capstone\Initial env Setup - Fall2022 Codebase\Local_env\uno-cpi\home\views.py, line 1375, in missionchart | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true |  |  | Sakthi | Issue | Working fine | 2023-02-11 | Fixed |  |  | 2023-02-19 | Closed by Sakthi
6 | Analytics - Charts | Focus Area Analysis chart showing error: KeyError at /issueaddress/ 'mission_color' Request Method: GET Request URL: http://127.0.0.1:8000/issueaddress/ Django Version: 4.1.2 Exception Type: KeyError Exception Value: 'mission_color' Exception Location: C:\Karpagam\Capstone\Initial env Setup - Fall2022 Codebase\Local_env\uno-cpi\home\views.py, line 2040, in issueaddress | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Sakthi | Issue | Unable to verify | 2023-02-11 | Fixed |  |  | 2023-02-19 | Closed by Sakthi
7 | Analytics - Charts | Network analysis Chart - does not have any data | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Sakthi | Issue | Unable to verify | 2023-02-11 | Fixed |  |  | 2023-02-20
8 | Analytics - Charts | Partnership Intensity Analysis chart not opening | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Sakthi | Issue | Unable to verify | 2023-02-11 | Fixed |  |  | 2023-02-19 | Closed by Sakthi
9 | Projects | Project name not displayed properly. Text entered in paranthesis is not displayed in All Project, My Projects, My Drafts, Reports view, but the same is visible in edit project screen. Admin Panel shows unique project number and year the project was performed. | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Simran | Issue | Issue | 2023-02-11 | Open
10 | Partners | Partners page does not have 'Community partner registration facilities. | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | All |  | Simran/Sakthi | Requiement gap | Issue | 2023-02-11 | Open |  | Check with Mansi
12 | Administrator Menu | Admin Audit Log is not opening Page not found (404) Request Method: GET Request URL: http://127.0.0.1:8000/recent-changes/ Raised by: wagtail.views.serve Using the URLconf defined in UnoCPI.urls, Django tried these URL patterns, in this order: admin/ admin/login/ [name='adminlogin'] campusHome [name='campusHome'] CommunityHome [name='CommunityHome'] partners/ [name='partners'] map [name='map'] register-Campus-Partner-User/ [name='registerCampusPartnerUser'] registerCommunityPartnerUser/ [name='registerCommunityPartnerUser'] signupuser/registerCampusPartnerUser/ [name='registerCampusPartnerUser'] signupuser/registerCommunityPartnerUser/ [name='registerCommunityPartnerUser'] signup/ [name='signup'] signupuser/ [name='signupuser'] uploadProject/ [name='upload_project'] uploadCommunity/ [name='upload_community'] uploadCampus/ [name='upload_campus'] uploadIncome/ [name='upload_income'] missionchart/ [name='missionchart'] issueaddress/ [name='issueaddress'] networkanalysis/ [name='networkanalysis'] | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin |  | Anh | Issue | Unable to verify | 2023-02-11 | Fixed |  | Ask Robyn on do we need Audit logs
13 | Navigation bar | When user is logged in, the User icon is displayed as Avatar | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Anh | Issue | Unable to verify | 2023-02-11 | Open
14 | Projects | When a new project is created, even if i logout and login using diffrent credentials, it shows the latest project created in All Projects, My Projects screens even if no filters are selected. | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Anh | Issue | Unable to verify | 2023-02-11 | Open |  | Check with Mansi
15 | Password reset | Unable to complete password reset functionality. It gives the below error. SMTPAuthenticationError at /password_reset/ (535, b'5.7.8 Username and Password not accepted. Learn more at\n5.7.8 https://support.google.com/mail/?p=BadCredentials i21-20020a02c615000000b003c48437c71asm4211571jan.44 - gsmtp') Request Method: POST Request URL: http://127.0.0.1:8000/password_reset/ Django Version: 4.1.2 Exception Type: SMTPAuthenticationError Exception Value: (535, b'5.7.8 Username and Password not accepted. Learn more at\n5.7.8 https://support.google.com/mail/?p=BadCredentials i21-20020a02c615000000b003c48437c71asm4211571jan.44 - gsmtp') Exception Location: C:\Users\kvelayutham\AppData\Local\Programs\Python\Python39\lib\smtplib.py, line 662, in auth | https://unomail-my.sharepoint.com/:w:/r/personal/spawaskar_unomaha_edu/_layouts/15/Doc.aspx?sourcedoc=%7B764F2736-0318-4408-801E-AB0D8FD1A2F8%7D&file=Open%20Issues%20-%20Local%20Env.docx&action=default&mobileredirect=true | Admin, Campus partner |  | Diana | Issue | Unable to verify | 2023-02-13 | Open
16 | Home Page | Homepage links leads to production pages
17 | Reports | Project Reports - leads to login form when reset filter is clicked
When a Campus partner user create a project using Create project Menu, the below details are not saved and thus not visible in the respective reports – Community partner, Focus Area etc. Mission area (Focus Area) Community partner Campus partner Even in Admin panel, these data are not captured.